* October
  + Technicolor
    - Proxy distribution agent – API definition - DONE
  + QCE
    - Functional test planning begins Oct 13 - BEGAN
* November
  + Technicolor
    - Security manager utility v0.5 Nov 3 - DONE
* December
  + QCE
    - ASACORE-1170 (additional API calls) Dec 5
    - Permission management (SC) DC Dec 5
    - Permission management (TC) DC Dec 12
  + Microsoft
    - Finalize Threat Analysis effort
    - Complete design documentation
    - Complete design reviews with Alliance
  + Technicolor
    - Android sample v0.5 Dec 19
* January
  + QCE
    - Finalize test plan and test cases Jan 12
    - Functional Core testing begins Jan 12
    - Java android test applications (SC) DC Jan 26
  + Microsoft
    - Windows keystore implementation
    - Federated user identity prototype
    - Windows security manager sample application
* February
  + QCE
    - IOS sample test applications (SC) DC Feb 9
  + Technicolor
    - Security Manager Utility v1.0 Feb 20
    - Android sample v1.0 Feb 20
  + Microsoft
    - Optional credential management plug-in model
    - Test case documentation
  + Integration testing needs to begin
    - Requires additional planning and coordination between contributors
* March
  + Test effort completes Mar 31
* April
  + Security 2.0 included as part of the 15.04 Core release